## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Srinivas | 2026-09-03 | Chroma rejected indexing 23,000+ chunks from a large CSV in one call — batch size limit exceeded | Sprint 1 | Srinivas | Standards | Split chunks into batches of 4000 before calling add_texts() | 2026-09-03 | Closed | Chroma has a hard max batch size of ~5461 per call
2 | Srinivas | 2026-09-03 | Same chunk appeared 3 times in search results after repeated runs — vectorstore wasn't clearing old data | Sprint 1 | Srinivas | Logical | Reordered imports so shutil.rmtree() runs before Chroma opens a connection to the vectorstore folder | 2026-09-03 | Closed | Root cause: import order + file locking, not a search bug
3 | Srinivas | 2026-09-12 | openai client crashed on every LLM call with Client.__init__() got an unexpected keyword argument 'proxies' | Sprint 2 | Srinivas | Standards | Pinned httpx==0.27.2 in requirements.txt | 2026-09-12 | Closed | Transitive dependency conflict, not a code bug
4 | Srinivas | 2026-09-12 | Gemini model gemini-2.5-flash returned 404, deprecated by Google | Sprint 2 | Srinivas | Standards | Updated model string to gemini-3.6-flash | 2026-09-12 | Closed | Confirmed via Google's own error message
5 | Srinivas | 2026-09-12 | blocker_agent missed blocked CSV tasks; scope_agent responsibilities went empty after widening retrieval query | Sprint 2 | Srinivas | Logical | Added exact metadata filtering and multi-query merge to retrieval | 2026-09-13 | Closed | Root cause: single semantic query can't satisfy two distinct sub-questions
6 | Srinivas | 2026-09-13 | LLMClient accepted malformed/non-JSON text as a successful response since no exception was raised | Sprint 2 | Srinivas | Logical | Added JSON validation inside the fallback loop | 2026-09-13 | Closed | A response that doesn't error isn't necessarily usable
7 | Srinivas | 2026-09-13 | OpenRouter's openrouter/free auto-router randomly selected a content-safety classifier model instead of a chat model | Sprint 2 | Srinivas | Standards | Pinned to a specific named model instead of the random auto-router | 2026-09-13 | Closed | Confirmed via OpenRouter's own docs: router "selects free models at random"
8 | Srinivas | 2026-09-13 | Guessed OpenRouter model slug was invalid (400 — not a valid model ID) | Sprint 2 | Srinivas | Standards | Verified real model slug against live provider pages before reuse | 2026-09-14 | Closed | Plausible-sounding model names aren't guaranteed to exist
9 | Srinivas | 2026-09-14 | OpenRouter reasoning model returned empty content, causing a NoneType crash | Sprint 2 | Srinivas | Logical | Added explicit max_tokens and empty-content guard with a clear error message | 2026-09-14 | Closed | Reasoning models can exhaust token budget before writing a final answer
10 | Srinivas | 2026-09-15 | Cloudflare Workers AI model @cf/meta/llama-3.1-8b-instruct deprecated (410 error) | Sprint 2 | Srinivas | Standards | Switched to Cloudflare's recommended @cf/meta/llama-4-scout-17b-16e-instruct | 2026-09-15 | Closed | Confirmed via Cloudflare's own changelog
11 | Srinivas | 2026-09-28 | doc_gen_agent.py failed with all 3 providers reporting missing API keys, despite .env being correctly configured | Sprint 3 | Srinivas | Standards | Added load_dotenv() call to doc_gen_agent.py — each independent entry point must load .env itself | 2026-09-28 | Closed | Root cause: .env is not inherited across separate script runs, even in the same terminal session
12 | Srinivas | 2026-09-30 | Installing Streamlit caused a protobuf gencode/runtime version mismatch, crashing the app on chromadb's import | Sprint 3 | Srinivas | Standards | Upgraded and pinned protobuf>=6.33.5 in requirements.txt | 2026-09-30 | Closed | New dependency (Streamlit) shifted an existing transitive dependency out of alignment
13 | Srinivas | 2026-09-30 | Streamlit dashboard displayed results from previous terminal runs before any pipeline button was clicked in the current session | Sprint 3 | Srinivas | User Interface | Gated each tab's display behind a st.session_state flag, set only when its corresponding button is clicked | 2026-09-30 | Closed | Reading from disk on every rerun is correct for persistence, but needed a session-scoped visibility gate for demo clarity
14 | Srinivas | 2026-10-02 | Custom CSS on Streamlit internal wrappers caused doubled/ghosted card borders across the entire UI | Sprint 4 | Srinivas | User Interface | Replaced with native Streamlit theme config | 2026-10-02 | Closed | Resolved by removing custom CSS overrides and using the native Streamlit theme configuration to maintain consistent UI styling and avoid conflicts with internal wrappers.
15 | Srinivas | 2026-10-03 | New incrementally-added file content wasn't reflected in agent output despite correct indexing | Sprint 4 | Srinivas | Logical | Guaranteed latest file batch always included in agent context, not just relying on semantic ranking | 2026-10-03 | Closed | Resolved by ensuring the latest uploaded file batch is always included in the agent context, preventing newly added content from being missed due to semantic-ranking limitations.
16 | Srinivas | 2026-10-03 | Initial upload widget silently reset data/raw on every Streamlit rerun, undoing manual edits and incremental additions | Sprint 4 | Srinivas | Logical | Gated the widget's write logic behind a session-state flag | 2026-10-03 | Closed | Resolved by gating the widget's write operation with a session-state flag, preventing unintended data resets during Streamlit reruns and preserving manual/incremental updates.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others